## RAID LOG
| RAID Log | [9 empty] | Total | Critical | High | Moderate | Low | Negligible
[10 empty] | Risk | 1 | 0 | 0 | 0 | 0 | 0
| Project title: | Absence of insights for the relationship between student's economic background, academic performance, competence and expected salary. |  | Project Id: |  | Project Manager: | Harshada Topale |  |  | Assumption | 1 | 0 | 0 | 0 | 0 | 0
[10 empty] | Issue | 2 | 0 | 0 | 0 | 0 | 0
| DOCUMENT VERSION: | 4.00 |  | Last Updated date: | 2025-06-16 | Project Team Lead: | Pranav Patel |  |  | Dependency | 1 | 0 | 0 | 0 | 0 | 0
| Select … |  |  |  |  | Select … | Risk Priority Number | Open/Closed |  |  | 5 |  |  |  |  | 0
| RAID Category | Description | Impact | Mitigation | Owner | Priority | RPN (for risks) | Status
1 | Risk | Infrastructure breakdown | Impact on the project schedule and cost. | Have a dedicated maintenance team for the project .The project budget should be considered. Regular backups on servers or cloud | Project Team Lead | High | 1 | Closed | Risk
2 | Assumption | The data is represents the most recent student demographics and no additional sources of data are needed | Inaccurate results | Data collection conducted quarterly or half yearly | Project Team Lead | Low |  | Closed | Assumption
3 | Issue | Data Cleaning – Duplicate values in the table. | Skewed results | Solved by removing duplicates by the Email IDs | Project Team Lead | Moderate |  | Closed | Issue
4 | Issue | Data Transformation – presence of multiple values for the column related to Promotion channels. | Skewed results | Selecting the first value | Project Team Lead | Moderate |  | Closed | Dependency
5 | Dependency | Presence of PowerBI to create & view the insights | Inability to create and view insights | Installing PowerBI on the system | Project Team Lead | Moderate |  | Closed
6 | [8 empty] | Open
7 | [8 empty] | Closed
8
9 | [8 empty] | Critical
10 | [8 empty] | High
11 | [8 empty] | Moderate
12 | [8 empty] | Low
13 | [8 empty] | Negligible
14
15
16
17
18
19
20
21
22
23
24